| Goal # 1: Promote connectivity among GCC members |  |  |  |  |
| --- | --- | --- | --- | --- |
| Host two Urban Sustainability Workshops for all GCC members each year |  |  | Spring (Northern CA) Fall (Southern CA) |
| Promote Member Accomplishments on Website and through GCC communications |  |  | New Website in Progress |
| In concert with member priorities, create one Press Event per year that features innovative GCC Best Practices |  |  | TBD |
| Host issues calls at least once every two months so GCC members can strategize on significant statewide issues |  |  | Consider revising to “as requested” by members |
| Increase connectivity between GCC, USDN and other organizations that share similar objectives |  |  | In progress |
| Goal # 2: Foster resource sharing |  |  |  |  |
| Continually update and improve accessibility of Best Practices on GCC’s website and increase social media and other outreach mechanisms to promote website |  | New Website in Progress |
| Provide templates of support/oppose letters for relevant state policy |  | Coordination as needed- example Letters of support for CPSC and San Francisco |
| Advocate for adoption of GCC Best Practices by as many members as possible |  | Typically occurs via Issue Call and Workshops |
| Evaluate potential GCC membership by other local governments that meet the basic GCC criteria (Climate Action Plan and/or Sustainability Plan approved or in process; willingness to actively support innovative policies and programs; willingness to share best practices) and have full Steering Committee support before approval |  | In progress- Discuss at 2015 Spring Workshop; Reconsider a replacement t for Urban Environmental Accords |
| Goal # 3: Produce a sustainable infrastructure for GCC |  |  |  |  |
| Establish GCC as an independent nonprofit organization -501(c)(3) |  | SEE Separate Timeline- Filing to be completed by October 2015 |
| Review current Budget – percent of funding from dues and grants Roles of GCC Members and GCC staff Identify additional potential funders and develop relationships |  | Ongoing- Member Participation is needed |
| Investigate crowd source funding as a means to support specific projects |  |  |
| Develop and submit grant proposals for activities under Goal # 4 |  | Submitted 2 proposals in 2015- one for water and one for energy |
| Goal # 4: Promote innovation and collaboration |  |  |  |  |
| ENERGY Energy Data: Access, Standardization and Disclosure Community Choice Aggregation |  |  |
| WATER/ DROUGHT RESPONSE Mandatory Conservation Building Local Supplies |  |  |
| CLIMATE ADAPTATION and RESILENCE Best Practices |  |  |
| SOLID WASTE Product Stewardship, including Pharmaceutical Waste Solid Waste Franchise Issues |  |  |
| TRANSPORTATION Electric Vehicle Infrastructure Multimodal Best Practices |  |  |
| FINANCIAL LEVERS Credit Rating Agencies- criteria for Resilient Communities Divestment from Fossil Fuels Local Incentives __________________________________________________________________________________ |  |  |

GOAL 3- Establish GCC as an independent nonprofit organization -501(c)(3)

| Major Category | Managing Director Time | 501 ( c ) ( 3 ) Committee Time | Approximate Begin and End | Comments |
| --- | --- | --- | --- | --- |
| Establish Bylaws- this is a critical part and may require the most time since it is an iterative process between the Managing Director and the Steering Committee for development of drafts, review, revisions, and final approval. | 20-30 hours | 10 hours- discuss, review, revise, (repeat as needed), approval | Begin: Mid-June Complete: Late August | Membership Bylaw Provisions for Public Benefit Corporation- Article 1- Offices Article 2- Purposes Article 3- Directors Article 5- Committees Article 8- Fiscal Year Article 13- Members- qualifications, dues, etc.. Written Consent of Directors Adopting Bylaws Review by an attorney or someone very knowledgeable about establishing Bylaws. |
| File Articles of Incorporation- this is based on the Bylaws | 3-5 hours | 1-2 hours- review, Q&A | Begin: August End: August | This is actually the first step toward formal filing, and this will be submitted to the CA Secretary of State |
| Apply for Federal Tax Exemption- this is a very long form and may take a while to complete. However, it is also based on the Bylaws. | 8-10 hours | 2-3 hours- review, Q&A | Begin: August End: September |  |
| Set Up Corporate Records Book | 20 hours |  | Begin: January 2016 End: March or April 2016 | This is where we may need some administrative assistance from an experienced person. It might be possible to get that assistance from the Local Gov Commission. |
| Transfer Assets from Financial Sponsor | 4 hours—paperwork and follow-up. |  | April 2016 | This process is not hard, but the actual transfer may take a while to complete. |
| File additional paperwork and issue member certificates, etc… |  |  |  | Board Meeting; other forms for bulk mailing, etc… |